## read me
How to use this template
Yellow cells are yours to edit. Everything else is a formula — leave it alone.
1. Set the project start date in the yellow cell at the top of the 'tasks' sheet.
2. Type your tasks: name, how many days, and which task IDs must finish first.
3. The start dates work themselves out and the bars draw themselves.
Columns the chart uses
Start and Finish are calculated. Start is the earliest this task can begin once
its predecessors are done. Weekends are skipped.
To pin a task, put an x in the Pin column and type the date you want in Start.
Everything else still calculates around it, and the scheduler treats a pinned
task as fixed. That is the same thing dragging a bar does in the tool.
The one rule
List a task BELOW the tasks it depends on. If you do not, the Check column
says so.
Columns the scheduler uses
Predecessors — the task IDs that must finish first, comma separated. 6,7 means
this task waits for both 6 and 7.
Resource · Crew/day — who does the work and how many of them it takes per day.
This sheet works out the dates. It does not work out the crew.
It has no idea that you only have 3 crew. The load panel below the chart shows
where you are over — it does not fix it.
If you want the dates worked out properly — the critical path, the earliest finish
that your actual crew size allows, or the same deadline with the daily peaks
levelled out — upload this file to the free scheduler:
https://gantt.kindoflost.com
It reads these exact sheets, solves it, and hands the file back to you with:
· the 'solution' tab filled in — every task's new start, finish, float, and
whether it sits on the critical path
· the Start column on this sheet overwritten with the solved dates, so the
bars you are looking at redraw themselves and the red goes away
· a run summary: what it would have taken with unlimited people, what it
actually takes with yours, and the difference
No signup, nothing to install.
Two modes, set on the 'parameters' sheet
finish_sooner — you have 3 electricians, not 9. What is the earliest this can finish?
smooth_load — keep the finish date, but stop the crew count spiking to 12 one week
and dropping to 2 the next.
Limits: 60 tasks, 95 days, finish-to-start links only, in this template.

## tasks
Project Gantt Chart |  |  |  | Project start |  | 2026-09-07
Free template from kindoflost.com — fill in the yellow cells, the bars draw themselves.
[10 empty] | Sep | [23 empty] | Oct | [30 empty] | Nov | [29 empty] | Dec
ID | Task | Days | Predecessors | Resource | Crew/day | Start | Finish | Pin | Check | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | helper: max predecessor finish | helper: predecessors listed | helper: predecessors found
1 | Site setup and fencing | 3 |  | Crew | 2 | 2026-09-07 | 2026-09-09 | [97 empty] | 0 | 0 | 0
2 | Demolition | 5 | 1 | Crew | 3 | 2026-09-10 | 2026-09-16 | [97 empty] | 2026-09-09 | 1 | 1
3 | Excavation | 4 | 2 | Excavator | 1 | 2026-09-17 | 2026-09-22 | [97 empty] | 2026-09-16 | 1 | 1
4 | Foundations | 6 | 3 | Crew | 3 | 2026-09-23 | 2026-09-30 | [97 empty] | 2026-09-22 | 1 | 1
5 | Underground plumbing | 4 | 3 | Plumbers | 2 | 2026-09-23 | 2026-09-28 | [97 empty] | 2026-09-22 | 1 | 1
6 | Slab pour | 2 | 4,5 | Crew | 3 | 2026-10-01 | 2026-10-02 | [97 empty] | 2026-09-30 | 2 | 2
7 | Framing | 10 | 6 | Crew | 3 | 2026-10-05 | 2026-10-16 | [97 empty] | 2026-10-02 | 1 | 1
8 | Roofing | 5 | 7 | Crew | 3 | 2026-10-19 | 2026-10-23 | [97 empty] | 2026-10-16 | 1 | 1
9 | Rough electrical | 6 | 7 | Electricians | 2 | 2026-10-19 | 2026-10-26 | [97 empty] | 2026-10-16 | 1 | 1
10 | Rough plumbing | 5 | 7 | Plumbers | 2 | 2026-10-19 | 2026-10-23 | [97 empty] | 2026-10-16 | 1 | 1
11 | Windows and exterior doors | 4 | 7 | Crew | 2 | 2026-10-19 | 2026-10-22 | [97 empty] | 2026-10-16 | 1 | 1
12 | Insulation | 3 | 9,10,11 | Crew | 2 | 2026-10-27 | 2026-10-29 | [97 empty] | 2026-10-26 | 3 | 3
13 | Drywall | 7 | 12 | Crew | 3 | 2026-10-30 | 2026-11-09 | [97 empty] | 2026-10-29 | 1 | 1
14 | Interior painting | 5 | 13 | Painters | 2 | 2026-11-10 | 2026-11-16 | [97 empty] | 2026-11-09 | 1 | 1
15 | Flooring | 4 | 14 | Crew | 2 | 2026-11-17 | 2026-11-20 | [97 empty] | 2026-11-16 | 1 | 1
16 | Final electrical fit-out | 3 | 14 | Electricians | 2 | 2026-11-17 | 2026-11-19 | [97 empty] | 2026-11-16 | 1 | 1
17 | Plumbing fixtures | 3 | 14 | Plumbers | 2 | 2026-11-17 | 2026-11-19 | [97 empty] | 2026-11-16 | 1 | 1
18 | Exterior painting | 6 | 8,11 | Painters | 2 | 2026-10-26 | 2026-11-02 | [97 empty] | 2026-10-23 | 2 | 2
19 | Driveway | 5 | 8 | Crew | 2 | 2026-10-26 | 2026-10-30 | [97 empty] | 2026-10-23 | 1 | 1
20 | Landscaping | 6 | 19 | Crew | 1 | 2026-11-02 | 2026-11-09 | [97 empty] | 2026-10-30 | 1 | 1
21 | Punch list and handover | 3 | 15,16,17,18,20 | Crew | 2 | 2026-11-23 | 2026-11-25 | [97 empty] | 2026-11-20 | 5 | 5
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
[7 empty] | 0 | [97 empty] | 0 | 0 | 0
| Daily resource load |  | red = more than you have that day |  | Have
| Crew |  |  |  | 3 |  |  |  |  | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 2 | 4 | 4 | 4 | 5 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Electricians |  |  |  | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Plumbers |  |  |  | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Painters |  |  |  | 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Excavator |  |  |  | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## resources
Resources
How many of each you actually have per day. This is what the scheduler treats as a hard cap.
Resource | Available per day | Notes
Crew | 3 | General labour
Electricians | 2
Plumbers | 2
Painters | 2
Excavator | 1 | Single machine

## parameters
Parameters
parameter | value | description
Mode | finish_sooner | finish_sooner = earliest finish that respects the crew caps. smooth_load = keep the deadline, flatten the daily peaks.
Deadline |  | Only used by smooth_load. Leave blank to hold the finish date the tool computes for finish_sooner.
WorkDaysPerWeek | 5 | 5 = skip weekends. 7 = work straight through.
SolveSeconds | 120 | How long the solver may search before returning its best answer.
AllowSplitting | no | Can a task pause and resume, or must it run start to finish?

## solution
task_id | task | resource | crew_per_day | start | finish | float_days | critical | days_moved | waiting_on | float_unlimited_crew | Run summary
The scheduler fills this in. Empty = nothing solved yet.
[11 empty] | Mode | finish_sooner or smooth_load
[11 empty] | Optimality | proved optimal, or the best found inside the time limit
[11 empty] | CPM finish | when it would end with unlimited people
[11 empty] | Scheduled finish | when it ends with the crew you actually have
[11 empty] | Days added by resource limits | the gap between those two — the number nobody else shows you
[11 empty] | Tasks that cannot be delayed | zero float once the crew you actually have is taken into account
[11 empty] | Peak load before | worst day, as uploaded
[11 empty] | Peak load after | worst day, after scheduling
Overloaded days before
[11 empty] | Overloaded days after | should be zero